Cwm Taf Morgannwg Social Services and Wellbeing Partnership Board

TRANSFORMATION PROGRAMME RISK LOG (PERIOD COVERED: SEPTEMBER 2019)

| Date raised | Category | Description of risk | Probability H/M/L | Impact H/M/L | Risk Status | Mitigation | Owner | Actions Taken/ Update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| September 2019 | Planning | Interdependencies between projects and boundaries not properly understood and may impact on overall progress and future sustainability. | M | H | Amber | - Identify interdependencies and assess impact on the overall programme. - Manage interdependencies to minimise any detrimental impact. - Transformation Steering Group established; | Anthony Hughes | - Financial Governance document to be submitted to TLG 29th October 2019 -Finance, Workforce, Measurement & Evaluation working groups to be set up |
| September 2019 | Performance and Evaluation | Tight timescales around evaluation could impact on quality of outcome and limit learning and improvement | M | H | Amber | - Evaluation tender produced and agreed at Transformation Steering Group; | Anthony Hughes | -Evaluation Procurement Panel to meet mid November 2019 - Set up Measurement & Evaluation working group to develop performance framework and link with appointed Evaluation Consultants |
| September 2019 | Performance and Evaluation | Failure to measure the right metrics will limit impact on the expected Programme outcomes, impacting on sustainability | M | H | Amber | - Assess baseline measures - Align baselines to expected outcomes - Develop logic models via support from Evaluation Consultants | Anthony Hughes |  |
| September 2019 | Resource Capacity and Capability to Deliver | Delay in recruiting staff to new delivery models will slow down delivery, limit evidence base resulting in poor sustainability plans. | H | H | Red | - Workforce Working Group set up and lead post appointed; - Recruitment trackers in place; - Monthly highlight reports to report progress | Sara Mason | -Workforce working group to take place 29th October 2019 |
| September 2019 | Resource Capacity and Capability to Deliver | Ability to develop and maintain an accurate programme implementation plan | M | H | Amber | - Programme milestones to be created by the PMO which will be regularly reviewed and used to drive progress. | Anthony Hughes | -Programme Managers meeting 25th October 2019 |
| September 2019 | Communication | Robust communications not being in place causing a detrimental impact on the programme from a range of stakeholder groups | M | H | Amber | - Communication plan currently being developed with support from Head of Communications. | Anthony Hughes/ Sarah Mills/ Julia Sumna | -Report to TLG requesting the recruitment of a Communications Officer covering Transformation and ICF Fund |

|  |  | Impact |  |  |
| --- | --- | --- | --- | --- |
|  |  | low | medium | high |
| Probability | low |  |  |  |
|  | medium |  |  |  |
|  | high |  |  |  |

CATEGORY

Planning

Performance and Evaluation

Resource Capacity and Capability to Deliver

Communication