Quarter 2 - Reporting Proforma for NHS Planning 2019-20

| Name of Organisation | Cwm Taf Morgannwg University Health Board |
| --- | --- |
| Director of Planning | Ruth Treharne |
| Submission date: | 11 October 2019 |

Include RAG Status in quarter just completed and the next quarter ahead

| R | Milestones not achieved or off profile to achieve in the period: corrective action required or new milestones to be agreed |
| --- | --- |
| A | Milestones off profile to achieve in the period: corrective action can be taken to achieve within the agree timeline. |
| G | Milestones achieved or on profile to achieve in the period: maintain trajectory |

Please evidence below how your organisation is delivering its specific accountability conditions and raise any other matters by exception.

This template must be submitted to HSS-PlanningTeam@gov.wales quarterly. The deadline date for quarter 2 is below:

Quarter 1 – 11 October 2019

| Accountability Conditions |  |
| --- | --- |
| Specific conditions | Evidence |
| - the Board must accelerate and strengthen governance and quality throughout the organisation. This must include having a robust improvement plan in place with clear milestones and outcomes to ensure rapid progress is made against key areas (including developing the organisational capacity and capability for improvement and an associated QI hub, maternity services (including achievement of the milestones set by the Independent Oversight Panel), serious incident and concerns management, Board leadership, organisational development and governance) and providing evidence of this through monthly reporting arrangements. | - DU, HIW/WAO, HIW and other reviews/reports being considered through governance arrangements and reporting to QSR Committee throughout Oct/Nov 2019 with associated management responses/action plans. - Quality & Patient Safety Programme Director leading implementation of the Quality and Patient Safety Governance Framework which is on target. - Weekly oversight of serious incident and concerns management, some improvement in performance in terms of 30 and 60 day response times. - Following IMSOP and Welsh Government workshop in August 2019, a performance and assurance framework has been agreed, aligning performance management to the HIW domains of Safe and Effective Care, Quality of Management and Leadership and Quality of Patient Experience. - Offer of support interventions by delivery unit welcomed, currently being scoped. RAG: Green - Programme Management arrangements being put in place to address issues falling under Targeted Intervention and Special Measures (Appendix 1 - presented to Board Sept 2019). - Plans for realignment of the organisational resource related to quality in development as part of the organisation’s structures work. RAG: Amber |
| - Ongoing assurance in relation to the transitional arrangements for the Bridgend boundary change, including organisational development arrangements required and financial implications; | - Update on the Legacy Statement from the Bridgend Boundary Quality and Patient Safety Work Stream presented to the Quality Safety & Risk Committee 5 September 2019 - The Joint Swansea Bay /CTM UHB Executive Group is meeting regularly to oversee the delivery of the ongoing joint work relating to the Bridgend Boundary Change. - Following the analysis the consultation on CTM UHB organisational structures in July, an engagement exercise is underway to develop an new operational model and subsequent organisational structure. RAG: Green The outcome of arbitration is covered with the Finance section |
| - Ongoing assurance and sustained improvement in the health board’s role as a provider of specialist CAMHS services to your population and for those services you provide on behalf of other health boards; | Ty Llidiard Tier 4 CAMHS Inpatient Unit. Following the approval of funding during 2018/19, the works to enhance the security and reduce ligature risks on the Unit have been largely completed, with a small number of outstanding works now being finished off. The Unit is therefore now in a possible to review the interim admission agreed with WHSSC, with a view to returning to previous criteria. This will tie in with the discussions arising from the current WHSSC consultation regarding the updated service specification for CAMHS tier 4 inpatient units, due to close on the 18th October. The Unit continues to face challenge in terms of being requested to admit patients outside the admission criteria and difficulty in discharging certain patient groups, particularly where there are social care requirements. It is understood that there is work ongoing within Welsh Government to review the provision of services within health and social care and this focus on alignment between services and planning is welcomed by the service. Specialist CAMHS As at 1st October 2019, the unverified position, in CTM UHB was 85.3% and in Swansea Bay UHB 96.7%. Therefore the 80% target is currently being met across the two Health Boards. Waiting list initiatives are ongoing to maintain this position whilst substantive staff are being recruited from the funding received from Welsh Government. As reported previously in Swansea Bay there is a capital project ongoing to move all Swansea CAMHS staff to Neath Port Talbot Hospital so that all staff will work from one base and to support the implementation of a single point of access. RAG: Green |
| - Increased clarity on actions, deliverables and milestones for all aspects of the plan must be in place and scrutinised by the Board; and | Regular reporting on achievement of key deliverables and milestones is achieved via the Integrated Performance Report, Quality Governance Framework and finance report. Over recent months the Board scrutiny has focussed on issues relating to Targeted Intervention and Special Measures as core, featuring as standard agenda items on Board meetings and QSR Committee meetings. |
| - Regional planning commitments and milestones must be transparent and accelerated. | The South Central and East Wales Regional Planning and Delivery Forum is in the process of implementing the following regional service changes: - Paediatrics, Obstetrics & Neonatology Services: - Ear, Nose and Throat Services; - Vascular Centralisation; - Diagnostics; and - Ophthalmology. The detail of the change is contained within most recent Forum paper attached at Appendix 2 RAG: Amber |
| The headings below encompass generic conditions set out in your accountability letter. These can be completed at your liberty. Issues defined by your organisation as ‘by exception’ should be included. |  |
| Quality - by exception |  |
| Quality issues are described in within section 1 above. |  |
| Collaboration (including RPB priorities) - by exception |  |
| The Cwm Taf Morgannwg Regional Partnership Board transformation funding was announced on 10 June 2019. Implementation of the former ‘Cwm Taf Stay Well in Your Community’ programme and Bridgend locality ‘Accelerating the Pace of Integrated Services’ programme. The programmes are now well underway and a revised Area Plan for the new Region is under development. RAG: Green |  |
| Performance - by exception |  |
| Appendix 3 is the Performance Summary Report from Board 26 September 2019 RAG: Amber |  |
| Finance - by exception |  |
| We are currently forecasting a breakeven position for 2019/20. The key risks to this forecast position are noted in Section 7 of our M5 Monitoring Return submission. The main risk is around a potential reduction to the £7.1m non-recurring allocation for the Bridgend arbitration. Any reduction to this allocation will represent a serious risk to the break-even forecast. We are currently reporting a £13.2m recurring deficit, which is an increase of £7.4m from the M4 deficit of £5.8m. This increase is attributable to the outcome of the Bridgend arbitration where no recurrent funding has been confirmed against the Bridgend recurrent deficit of £7.4m. It is important to note that the revised forecast recurring deficit of £13.2m assumes full delivery of the £11.8m recurring savings target for 2019/20. The latest recurring savings gap is £3.0m (£2.8m at M4) and a key driver for this position is the ‘delay effect’ due to the Bridgend boundary change. Urgent meetings are taking place within the Health Board to regain traction and focus on savings delivery. In light of the seriousness of the BG position, further work is ongoing to separately report the BG financial position. We would welcome further discussions with WG on the outcome of the BG arbitration on the forecast positions. RAG: Amber |  |
| Other comments/issues by exception |  |