| TARGETED INTERVENTION PROGRAMME HIGHLIGHT REPORT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Completed by: | Chris Darling |  | Reporting period: |  | February 2020 | To: | March 2020 |
| Date Completed: |  | 11/03/2020 |  |  | Next Review Meeting: |  | 22 April 2020 |
| Current status: |  | Headlines: |  |  |  |  |  |
| R. A. G. | - Progress in all areas (milestones achievement reasonable although some slippage in some areas) - Maturity matrices final drafts to reflect WG feedback - Maturity matrices initial self-assessment populated for Trust and Confidence, Leadership and Culture, Quality and Governance and presented to WG on 28/02/20 - Judgement framework and self-assessment process being mapped out |  |  |  |  |  |
| Key Achievements This Quarter |  |  |  | Project Plan: Proposed Achievements Next Quarter |  |  |  |
| - New style of public engagement has commenced with talking cafes. - HIW/WAO Joint Review response updated in relation to short term actions - Values and Behaviours Phase 2 feedback to staff took place over a number of sessions at the end of Feb 2020 - Maturity Matrix completed for Trust and Confidence, Leadership and Culture and Quality and Governance - The Consultation Institute commissioned to undertake some guidance and advice support around embedding engagement and involvement with stakeholders. |  |  |  | - Further work on Let’s Talk Culture planned - Risk Management Strategy to be ratified at Board - Implement Quality Impact Assessment process - Use quality dashboard with narrative - Implement initial leadership offering for senior leaders (multi-disciplinary) - Launch a day in the life of programme - Continue community engagement work - Re-launch monthly newsletter to stakeholders |  |  |  |
| Slippage and remedial action |  |  |  | Issue/Risks or concerns |  |  |  |
| - Some slippage with tasks and activity due to capacity relating to supporting COVID-19 |  |  |  | - Impact on capacity and pace to deliver if no additional resource - External and internal confidence remains low if negative Media coverage persists - Maintaining effective stakeholder relationships - Lack of ability to consolidate due to continued interventions - Impact of COVID-19 on capacity to respond to TI requirements over the coming months. |  |  |  |

| R | Red | Significantly behind schedule and requiring corrective action or decision to get back on track. |
| --- | --- | --- |
| A | Amber | Project behind schedule but within 2 weeks tolerance, or actions in hand to get back on track. |
| G | Green | On track or completed. |