|  | Maternity improvement – Quality of Women’s & Families Experience |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jan- Mar 2020 | Apr – June 2020 | July – Sept 2020 | Oct – Dec 2020 | Jan – Mar 2021 | Apr – June 2021 |
| My Maternity My Way (MMMW) | Recruitment drive for MMMW – commencing January 2020 | Meeting arranged 2020 | Targeted Completion date July 2020 - Outcome: Increase Lay Membership Support lay members to engage with Women and develop and strengthen monitoring role of the group commencing April 2020 Targeted Completion date July 2020 - Outcome: Develop and strengthen the role and capacity or the MMMY. 7.47 |  |  |  |
| Co-production | Ongoing - Work collaboratively with CHC Colleagues, Women & Families - ongoing engagement through various project board and public engagement events |  |  | Task and finish group will be established in February 2020 to scope opportunities of involving partners during labour in with a focus on a co- production approach involving staff and women & families | Targeted Completion date Dec 2020 - Outcome: agreed process for involvement of partners during labour |  |
| Engagement | 3rd Community engagement event is scheduled for 25th February 2020, feedback will be themed and actions identified –April 2020 | Completion date Marchl 2020: Finding s from engagement events will be shared with staff and public and used to drive service change Development of a co-produced community engagement plan for 2020– 2023 – commencing 27 March 2020 | Targeted completion date August 2020 Implementation of a three year engagement plan for Maternity Service 7.49, 7.50, 7.54 |  |  |  |
| Listening into action |  |  |  | PALS real-time feedback initiative will be piloted in antenatal clinics for a 12 month period, across four sites - commencing March 2020 Commence work on pilot for Maternity PREM with value based healthcare Team - commencing March 2020 | Targeted completion date April 2021 A range of opportunities will be available for women & their families to share their experiences 7.49, 7.50, 7.54 |  |