| Maternity improvement – Safe & Effective Care |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Jan-Mar 2020 | Apr – June 2020 | July-Sept 2020 | Oct – Dec 2020 | Jan-Mar 2021 | Apr-June 2021 |
| Putting things Right | Process implemented in line with PTR – ongoing monitoring required November 2019 Improve PTR Systems and processes 7.51 Ensure a system for identifying, grading, investigating & reporting, sharing learning from SI’s 7.19 (DU Rec) 7.21, 7.23 Managed in line with PTR, Flow charts clearly setting out process for SI’s, concerns, Claims will be developed by Feb 2020 – ongoing monitoring required Monthly regular sharing of learning events for staff Staff attendance at incident meetings Actively seek to remove the blame culture to allow staff to report & learn SI’s 7.20 Review, triage and learn from Clinical Reviews – commencing January 2020 – targeted completion date April 2021 | Ongoing Monitoring | Ongoing Monitoring through: - weekly concerns/SI’s reporting - Compliance against PTR monitoring undertaken weekly via Corporate Concerns Team - Scrutiny by Executive Team, HOM, MIB, - Progress monitored and scrutinised at Directorate Governance & Quality & Safety Forum - Timeliness of SI/complaints reviews and escalation |  |  |  |
| Quality improvement | Completion date May 2020 dedicated Pharmacy lead appointed Ensure all guidelines involving the administration of medication are up to date, Pharmacy Lead 7.2 Systems and processes in place for data collection and validation 7.1 – further work required - targeted completion date April 2021 Ongoing Monitoring via the PTR process De-briefing sessions are held after every incident and are facilitated by Consultants 7.12 Audit commenced mid-December with a focus on response times for consultants during emergency call outs 7.16 targeted completion date April 2021 Review the effectiveness of bereavement services 7.55 targeted completion date June 2020 | Reduce Induction of Labour rates commencing April 2020 – targeted completion date March 2021 Review effectiveness of bereavement services 7.55 - targeted completion date March 2021 | Reduce C Section rates – commencing April 2020 - targeted completion date March 2021 Baby abduction – commencing April 2020 - targeted completion date April 2021 Improve breast feeding support for Women – commencing April 2020 – targeted completion date Oct 2020 |  |  |  |
| Quality Control | Risk Register reviewed at board level 7.66 | Ongoing Monitoring |  | Ongoing Monitoring |  |  |
| Quality Planning | Ensure an environment of privacy and dignity is provided for women & families undergoing miscarriage 7.7 50 snagging list Anti-natal environment | Business case submitted, escalated to Senior Staff – too date there is no identified space available on the PCH |  |  |  |  |

Ongoing Monitoring