| Maternity improvement – Maternity Vision |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Jan- Mar 2020 | Apr – June 2020 | July – Sept 2020 | Oct – Dec 2020 | Jan – Mar 2021 | Apr – June 2021 |
| Maternity Vision | Develop Vision in consultation with key stakeholders e.g. IMSOP, CHC Women & families & neonatal board - January – April 2020 RCOG 7.58, 7.67 |  | Publish & Implemented Vision August 2020 |  |  |  |
| Strategic Planning | Attendance &Monitoring of key service delivery through Regional Obstetric Planning Board RCOG 7.31, 7.43, 7.69, | Ongoing Monitoring |  |  |  |  |