CTMUHB Approach to Risk Management – Key Milestones

| No. | Task | Timeline | Lead | Comments |
| --- | --- | --- | --- | --- |
| 1. | Confirm that one systematic approach to risk management is required i.e. move away from directorate datix risk register and corporate excel risk register with a view to integrated Datix-based register | Exec Meeting 27.01.20 | GG | Agreed. |
| 2. | Write and ask that the Service General Managers ensure Directorate risk registers are up to date, with risks articulated with; IF (this happens)……… THEN (impact will be)………. | By 31.01.20 | CD |  |
| 3. | Draft Risk Management Strategy and BAF to go to MB | 20.02.20 | CD/GG |  |
| 4. | Arrange a facilitated workshop with the ILG Directors and Service General Managers and H&S Lead to: - Review the draft Risk Management Strategy and BAF - Discuss/confirm proposed process to include triggers and hierarchy, how risks get into the corporate risk register and principle risks onto the BAF (informed by the IMTP) - The role of Management Board in owning the corporate risk register - The role of Board in overseeing the principle risks and BAF - Review risk scores on existing Directorate risk registers and reconcile to the current risk register | By 06.03.20 | CD |  |
| 5. | Work with Head of H&S to develop bespoke corporate risk register and reporting through Datix | 06.03.20 | CD/CB |  |
| 6. | Risk Management training to be provided to ILGs/Directorates to cover: - The basics of risk management - The process for escalating risk - The triggers for escalating risk - How risk will be discussed and reviewed at the ILGs and subsequently at Management Board | 16.03.20 – 15.05.20 | CD | Content of the training to be informed by task 3 |
| 7. | CTMUHB objectives to be confirmed via the IMTP 2020-23 process | 26.03.20 | Board |  |
| 8. | Principle risks in achieving the IMTP 2020-23 to be tested for inclusion in the BAF. | 27.03.20 – 30.04.20 | GG | Tested/approved at Management Board 15.04.20 |
| 9. | Introduce new risk management strategy and process – New Operating Model. - Datix to be used for Directorates, ILG risk registers to inform corporate risk register - New corporate risk register in use (via Datix) | From 01.04.20 | CD |  |
| 10. | Workshop on agreeing Board risk appetite | 30.04.20 | GG | Board Dev session |
| 11. | Agree principle risks to include in the BAF at Board, with controls, assurance and gaps identified. | 28.05.20 | GG |  |